## Activities
ACTIVITIES
Category | Work Package ID | Estimated Activities | Estimated Activities Description | Duration | Predecessor
1.1. Project Management (ACTIVITIES DONE IN PARALLEL)
| 1.1.1. | Project Plan / Communication management plan | Sharma Charul, Tomas Groher - To make sure team executes the project according to the set schedule, stays within your budget, and sticks to the planned activities Sharma Charul, Trishy Sin - Organize and document the process, types, and expectations of communications. | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.2. | Resource procurement and management plan | Sharma Charul, Tomas Groher - Creates and manage request for quotations (RFQs), requests for proposals (RFPs), requests for information (RFI) and managing supplier relationships | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.3. | Scope development | Sharma Charul, Tomas Groher - Develop a comprehensive scope document which will lay out every page, email, algorithm, and any other functionality in the app. The scope document will also include comprehensive timelines, hours and estimates. | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.4. | Risk Management Plan | Sharma Charul, Tomas Groher - Prepare/update doc to foresee risks, estimate impacts, and define responses to risks. | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.5. | Quality Management Plan | Sharma Charul, Tomas Groher - Define the project's quality policies, procedures, criteria for and areas of application, roles, responsibilities and authorities. | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.6. | Budget | Sharma Charul, Tomas Groher - Develop total estimated cost of completing the project over each phase | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.7. | Scheduling | Sharma Charul, Tomas Groher - Develop and oversee the listing of activities, deliverables, and milestones within the project. | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
| 1.1.8. | Document change control processes | Sharma Charul, Tomas Groher - Submit requests to stakeholders for review, approvals or denials | 4/15/2022 - 4/29/2022 (10 Days not including weekends) | NO
1.2. Business Requirements |  |  |  |  | YES (Activity 1.1)
| 1.2.1. | Business Requirements Collection / Evaluate existing processes | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Develop document to monitor user's needs and expectations, solution purposes, and any high-level constraints that could impact the successful deployment of our app. Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Review existing business process, document reviews, impact analysis and gap analysis | 5/2/2022 - 5/9/2022 (6 days no-weekends) | YES (Activity 1.2)
| 1.2.1.1. | Document all existing users and user roles | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Document all existing users and user roles | 5/10/2022 - 5/11/2022 (2 days) | YES (Activity 1.2.1)
| 1.2.1.2. | Regulatory compliance | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Develop a set of organizational processes, policies, and procedures that support internal/external compliance with the laws, rules, regulations, requirements | 5/12/2022 - 5/13/2022 (2 days) | YES (Activity 1.2.1.1)
| 1.2.1.3. | Audit control (including testing) | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Develop and implement procedures used to evaluate internal controls and vendor perdormance. Determine whether internal controls softare testing activities are sufficient to detect or prevent risks of material misstatements or app functionality failures. | 5/16/2022 - 7/15/2022 (50 days - no-weekends) | YES (Activity 1.2.1.2)
| 1.2.1.4. | Reporting | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be upper management and project sponsor | 5/17/2022 - 5/18/2022 (2 days) | YES (Activity 1.2.1.3)
| 1.2.1.4.1. | End user | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be end users | 5/19/2022 - 5/20/2022 (2 days) | YES (Activity 1.2.1.4)
| 1.2.1.4.2. | Management | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be mid-level managers and operational managers | 5/23/2022 - 5/24/2022 (2 days) | YES (Activity 1.2.1.4.1)
| 1.2.1.4.3. | System Administrative / Technical | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be tech managers and sys admins | 5/25/2022 - 5/27/2022 (3 days) | YES (Activity 1.2.1.4.2)
| 1.2.1.5. | 3rd party interconnects | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Monitor service performance from vendors based on SLA | 5/30/2022 - 5/31/2022 (2 days) | YES (Activity 1.2.1.4.3)
| 1.2.2. | Define new business rules | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Develop constraints, policies, SOPs to guide app development | 6/1/2022 - 6/2/2022 (2 days) | YES (Activity 1.2.1.5)
| 1.2.3. | Define new workflow | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Develop and implement workflow process or sequential tasks to carried out our app development based on user-defined rules or conditions. | 6/3/2022 - 6/6/2022 (2 days - no-weekends) | YES (Activity 1.2.2)
| 1.2.4. | Define specific UI requirements | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Capture the details of the user interface into a written document. | 6/7/2022 - 6/8/2022 (2 days) | YES (Activity 1.2.3)
| 1.2.5. | Define specific technology requirements | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Specify the design and architecture of the specific technical components needed in our app development, implementation, and operation | 6/9/2022 - 6/10/2022 (2 days) | YES (Activity 1.2.4)
| 1.2.6. | Requirements Documentation | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks - Define what is needed from the our new app | 6/13/2022 - 6/14/2022 (2 days) | YES (Activity 1.2.5)
1.3. Application Architecture and SW design and Implementation (ACTIVITIES TAKE PLACE IN PARALLEL) |  |  |  |  | YES (Activity 1.2)
| 1.3.1. | Application Architecture and SW Design and Implementation / Functional Specifications | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Provide the roadmap that describes the patterns and techniques used to design and build our application Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Document our app intended capabilities, appearance, and interactions with users in detail for software developers | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.1.1. | Process models | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Define the graphical representation of business processes or workflows of our app functionality | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.1.2. | User Interface | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Document the display screen, keyboards, and the appearance of our app | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.1.3. | nTier logic | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Define and document our app tiers, including presentation tier, a middle tier, and a data tier. | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.1.4. | Database model | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - define and document our the data model that determines the logical structure of our app database. | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.2. | Technical Specifications | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Outline the systemic and functional needs to meet for our app. This will allow us to achieve the desired features and functionalities | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.2.1. | Platform specifications | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Document the type of languages our app will reside on | 6/15/2022 - 7/15/2022 (22 days) | NO
| 1.3.2.2. | Development languages specifications | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks - Document the platform our app will reside on | 6/15/2022 - 7/15/2022 (22 days) | NO
1.4. Monitoring/Support and Final Signoff | 1.4. | Monitoring/Support and final Client Signoff | Sharma Charul, Tomas Groher, Peter Murthy - ongoing monitor Schedule and Cost Value, get approvals an signoff | 7/15/2022 - 8/15/2022 (20 days - no-weekends) | YES (All activities)