## WBS
WORK BREAKDOWN STRUCTURE

## WBS Dictionary
WORK BREAKDOWN STRUCTURE DICTIONARY
Work Package | Description | Resources | Responsible Party
1.1. Project Management | To make sure team executes the project according to the set schedule, stays within your budget, and sticks to the planned activities | Sharma Charul, Tomas Groher | internal
1.1.1. Communication management plan | Organize and document the process, types, and expectations of communications. | Sharma Charul, Trishy Sin | internal
1.1.2. Resource procurement and management plan | Creates and manage request for quotations (RFQs), requests for proposals (RFPs), requests for information (RFI) and managing supplier relationships | Sharma Charul, Tomas Groher | internal
1.1.3. Scope development | Develop a comprehensive scope document which will lay out every page, email, algorithm, and any other functionality in the app. The scope document will also include comprehensive timelines, hours and estimates. | Sharma Charul, Tomas Groher | internal
1.1.4. Risk Management Plan | Prepare/update doc to foresee risks, estimate impacts, and define responses to risks. | Sharma Charul, Tomas Groher | internal
1.1.5. Quality Management Plan | Define the project's quality policies, procedures, criteria for and areas of application, roles, responsibilities and authorities. | Sharma Charul, Tomas Groher | internal
1.1.6. Budget | Develop total estimated cost of completing the project over each phase | Sharma Charul, Tomas Groher | internal
1.1.7. Scheduling | Develop and oversee the listing of activities, deliverables, and milestones within the project. | Sharma Charul, Tomas Groher | internal
1.1.8. Document change control processes | Submit requests to stakeholders for review, approvals or denials | Sharma Charul, Tomas Groher | internal
1.2. Business Requirements | Develop document to monitor user's needs and expectations, solution purposes, and any high-level constraints that could impact the successful deployment of our app. | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1. Evaluate existing processes | Review existing business process, document reviews, impact analysis and gap analysis | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.1. Document all existing users and user roles | Document all existing users and user roles | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.2. Regulatory compliance | Develop a set of organizational processes, policies, and procedures that support internal/external compliance with the laws, rules, regulations, requirements | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.3. Audit control (including testing) | Develop and implement procedures used to evaluate internal controls and vendor perdormance. Determine whether internal controls softare testing activities are sufficient to detect or prevent risks of material misstatements or app functionality failures. | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.4. Reporting | Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be upper management and project sponsor | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.4.1. End user | Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be end users | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.4.2. Management | Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be mid-level managers and operational managers | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.4.3. System Administrative / Technical | Provide/develop high-level overview and reports on project progress, issues, resolutions using critical data from the project. The target audience will be tech managers and sys admins | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.1.5. 3rd party interconnects | Monitor service performance from vendors based on SLA | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.2. Define new business rules | Develop constraints, policies, SOPs to guide app development | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.3. Define new workflow | Develop and implement workflow process or sequential tasks to carried out our app development based on user-defined rules or conditions. | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.4. Define specific UI requirements | Capture the details of the user interface into a written document. | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.5. Define specific technology requirements | Specify the design and architecture of the specific technical components needed in our app development, implementation, and operation | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.2.6. Requirements Documentation | Define what is needed from the our new app | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Joe Zuromski, Algoworks | internal and external
1.3. Application Architecture and SW implementation | Provide the roadmap that describes the patterns and techniques used to design and build our application | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.1. Functional Specifications | Document our app intended capabilities, appearance, and interactions with users in detail for software developers | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.1.1. Process models | Define the graphical representation of business processes or workflows of our app functionality | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.1.2. User Interface | Document the display screen, keyboards, and the appearance of our app | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.1.3. nTier logic | Define and document our app tiers, including presentation tier, a middle tier, and a data tier. | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.1.4. Database model | define and document our the data model that determines the logical structure of our app database. | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.2. Technical Specifications | Outline the systemic and functional needs to meet for our app. This will allow us to achieve the desired features and functionalities | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.2.1. Platform specifications | Document the type of languages our app will reside on | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.3.2.2. Development languages specifications | Document the platform our app will reside on | Tomas Groher, Eileen Martinez, Tim Shah, Jen Varun, Jim Chum, Algoworks | internal and external
1.4. Client Signoff | approvals an signoff | Sharma Charul, Tomas Groher, Peter Murthy | internal